| NO | NAME | Rule details | Rule type |
| --- | --- | --- | --- |
| 1 | DOCUMENT SIZE | Must be less than 50MB | General |
| 2 | FILENAME | Must be in line with example: AO-400-10-S514-000004_01_IFC_20260402 Where “AO-400-10-S514-000004” is the Client Document Number, Where “01” is the current revision number, Where “IFC” is the status, Where “20260402” is the date of document issuance YYYYMMDD | General |
| 3 | NATIVE FILE | Refer to Free Attribute 4 or VMDL column AB, to ensure if the Native file is required, if yes, open it just be sure native file is working | Manual check |
| 4 | CRS COMPANY | It will be required for the document with CPY class 1 & 2 starting from Rev01; CRS to be verified before sent to CPY, CRS template cannot be modified, and fully completed; If any CPY class 3 document is commented by CPY, same logic | Manual check |
| 5 | PROJECT TEMPLATE | Must be used and cannot be modified, header and footer shall be applied for the rest of the document including Appendix, Annex and attachment: First pages are mandatory (for Word and Excel) and must be properly completed | General |
|  |  | If the project template has not been used, headers must be added from page 3 onwards, containing: Filename + Title + Page number of Total number of pages | VMDL |
| 6 | BOOKMARKS | Document having more than 50 pages should have bookmarks in the PDF. | General |
| 7 | COMMENT | No comments allowed on the PDF File or comments must be flattened | General |
| 8 | ATTACHMENT | No attachment allowed on the PDF File | General |
| 9 | LAYERS | No layers allowed on the PDF File | General |
| 10 | SEARCHABLE | Must be searchable, except for scanned certificates, reports, records or catalogs | General |
| 11 | TRACKCHANGES | Revision history section must be filled when rev is higher than 00. | General |
| 12 | LOGO | Project LOGO must be the present on the header. | General |
| 13 | DATE | Date format must be correct dd-Mmm-yyyy Ex: 07-Jun-2025 in the header. | General |
| 14 | NAMES | Format must be capital letter of the first name initial dot then Family name or Full name; example L. Yinghao or Lu Zongnan | General |
| 15 | SIGNATURES | Shall be Duly signed. Signatures Electronic (not protected) and scanned signatures will be allowed | General |
| 17 | CLASS | Must be in line with VMDL column “Kaminho Doc Class” under the example format “1/2”. The first figure represents the Contractor Class, the second figure represents the Company class. | VMDL |
| 18 | Footer | Footer on the first and second page must be: “The document is the property of COMPANY. It must not be stored, reproduced or disclosed to others without written authorization from the Company” | General |
| 19 | PAGINATION | Must be consistent with the document. Total number of pages must include Front pages. The check must also apply to the revision block history (in the PDF footer) | General |
| 20 | LANGUAGE | English, if the language of origin is not English, then the translation must be applied | General |
| 21 | REVISION HISTORY | Shall be Updated based on the Revision List on the first page. The data concerning the revisions before the current one, shall be in line with VMDL. | VMDL |
| 22 | TAGGING | Must be mentioned on the second page in “List of Tags” section | General |
| 24 | AS FABRICATED (ASF) | ASF status can only be issued if previous revision was IFC code 1 – Approved without comment | VMDL |
| 25 | STATUS | TO BE LOGIC CLASS 1 (IFR, IFA, IFC), CLASS 2 (IFR, IFC), CLASS 3 (IFI, IFI) | VMDL |

| NO | NAME | Rule details | Rule type |
| --- | --- | --- | --- |
| 26 | Vendor Name | Should be in line with Column B of the EXCEL. | VMDL |
| 27 | PO Nr | Should be in line with Column A of the EXCEL. | VMDL |
| 28 | PO Title | Should be in line with Column C of the EXCEL. | VMDL |
| 29 | Document Title | Should be in line with Column E of the EXCEL. | VMDL |
| 30 | Class | Should be in line with Column of the EXCEL (where header = “Kaminho Doc Class”) | VMDL |
| 31 | Discipline | Should be in line with Column J of the EXCEL (where header = “Discipline”) | VMDL |
| 32 | Contractor Doc Num | If available, Should be in line with Column L of the EXCEL Where header = “Contractor (CTR) Document Nr” | VMDL |
| 33 | System/Subsystem | Should be in line with Column “System / Subsystem” of the EXCEL | VMDL |
| 34 | Document Type | Should be in line with Column I of the EXCEL (where header = “Doc. Type”) | VMDL |
| 35 | Revision | Revision in Scanned Document shall not be in history of VMDL. | VMDL |
| 36 | Revision | Should be the last available in history + 1, under the format “XX” where the revision 5 should be formatted as “05” | VMDL |
| 37 | Status | Should be consistent with calculation summarized in the chart below where: Class is the current class on the Header of the PDF document, “Previous rev was” can be found in the Excel “VMDL” “Previous review code” can be found in the Excel “VMDL”. These 3 criteria will allow to read the next expected status that should be read in the Header of current PDF to be scanned. For example: if the scanned document has the class 2/3, if the previous rev was “IFR” If the previous CTR review code was “3 - Rejected”, then the expected status on current doc should be “IFR” Class; Previous rev was; 1 - Approved without comments; 2 - Approved with comments; 3 - Rejected. 1/2; IFA; IFC; IFC; IFA. 1/2; IFC; Not required; IFC; IFC. 1/3; IFR; IFA; IFA; IFR. 1/3; IFA; IFC; IFC; IFA. 1/3; IFC; Not required; IFC; IFC. 1/3; IFR; IFA; IFA; IFA. 2/2; IFR; IFC; IFC; IFR. 2/3; IFR; IFC; IFC; IFR. 3/3; IFI; IFI; IFI; IFI. 2/3; IFC; Not required; IFC; IFC. 2/2; IFC; Not required; IFC; IFC. 1/2; IFR; IFA; IFA; IFR. | VMDL |
| 38 | Status description | Should return by looking up the value corresponding to the Code (line 37) Code; Designation. IFR; Issued for Review. IFA; Issued for Acceptance. IFC; Issued for Construction. IFI; Issued for Information. | VMDL |
| 39 | Result review code | Last available CTR review code is available in VMDL and will be used to define item 12. | VMDL |
| 40 | First status | If the revision in the document is 00, status should correspond the look-up based on the class: CLASS; First rev. 1/1; IFR. 1/2; IFR. 1/3; IFR. 2/2; IFR. 2/3; IFR. 3/3; IFI. In VMDL file (excel file) 00 is replaced by “xx” | General |

| NO | NAME | Rule details | Rule type |
| --- | --- | --- | --- |
| 41 | « Rev. » In footer | Shall be compliant with VMDL revision field. The current revision of the document is not contained in the VMDL file. | VMDL |
| 42 | « Status » in footer | As per VMDL, all status data linked to the revisions shall be found in VMDL table (except the current document revision). | VMDL |
| 43 | « Date » in footer | All Dates format must be correct dd-Mmm-yyyy for example “07-Jun-2025” for all the revisions listed. | General |
| 44 | « Revision memo » in footer | Code; Designation. IFR; Issued for Review. IFA; Issued for Acceptance. IFC; Issued for Construction. IFI; Issued for Information. “Revision memo” shall correspond to the “Status” defined in criteria 42. | General |
| 45 | Rev and Date in the footer | All the info here relates to the upper line in the footer that must correspond to the current revision of the document, and therefore, it must respect the following criteria: The “Rev.” must be the same as in the header. The “Date” must be the same as in the header. | General |